Document No.: GANA-BR-2026-02 · Date: 2026. 7. 23. · Edition: 2nd Edition · Internal review only

GANA Group Rebranding Proposal

Shift of the Brand Axis and Execution Plan  |  2nd Edition

| Item | Details |
| --- | --- |
| Purpose | Request for approval of the shift in the group's external brand axis and the execution plan |
| Audience | Chairman and executive leadership |
| Scope | GANA R&D, GANA Cosmetic, Dr.Park CDMO, and affiliates |
| Approval requested | 4 items (Chapter 12, web scope). Item 1 requires no approval and can proceed immediately |
| Basis | Results of a full sweep of public registries conducted on 2026. 7. 22. |
| Structure | Part 1: Rebranding Direction (Chapters 1 to 7) · Part 2: Realization on the Web (Chapters 8 to 12) · Appendices A to G, analytical materials |

Executive Summary

This proposal recommends adding a proof axis, manufacturer identity, to the GANA Group's external brand. Nothing existing is removed. Anti-aging, the 'world's largest class' positioning, and all six affiliates stay in place. To these we add the proof (registrations) and the measurement standard (ruler) that hold the claims up under due diligence.

Not a filler company: bio-manufacturing infrastructure.

This is not a new direction. The company's own CDMO introduction video already says 'one of the world's largest and most advanced AAV production capacities', and internal technical validation materials already define the external language as 'not a filler company but bio-manufacturing infrastructure'. The most recently produced assets already stand on this axis, but the website and print materials have not yet caught up. What this proposal asks for, therefore, is not a change of direction but alignment.

The reason is simple. The phrase 'we care for aging' carries no distinguishing power because the cosmetics, filler, and health-functional-food industries all use it, and the moment it is spoken it invites the return question, 'how do you prove that.' Moving the axis to manufacturer identity does not make that question disappear. Instead it changes into an answerable form: 'show us the registrations.' GANA R&D Co., Ltd. is listed as the manufacturer on 38 product registrations across 5 jurisdictions, and the numbers can be produced on request.

The axis applies to different scopes depending on the layer. The surface and tissue layers are in the completed tense, proven by registration numbers. The cell and gene layer is described in the ongoing tense because construction is finished but cGMP has not been obtained. The framing is: we built it, and certification is targeted for 2026. We do not bind the two ends under a single subject.

There is one precondition, but its scope is narrow. Batch capacity appears as 5,000L, 6,000L, and 200,000L across different materials, which stems from each material being frozen at a different point in time. The required action is not a wholesale unification but a freeze of that figure, and the remaining work proceeds in parallel.

There are 4 approval requests, made concrete as realization on the web in Part 2 (Chapters 8 to 12). Item 1, immediate web cleanup, can begin at no cost regardless of the decision on the axis.

Nature of the Strategy: Positioning First

This proposal is a positioning strategy, not an advertising or promotion plan. Positioning is not one line item of marketing but the foundation on which all marketing rests. If the position is not set, no wording, channel, or budget layered on top will hold steady. So we set the axis before channels and campaigns.

In manufacturing-based B2B, it is right to first claim a clear position and then hold it with proof, rather than putting on a loud display. Our assets are not shouts but registrations, certifications, and track record, and these carry more force when confirmed than when trumpeted.

There are two grounds for believing this approach works.

First, the evidence of results. GANA R&D grew for 13 years on nothing more than the current level of website. This does not mean the web is unnecessary; it is evidence that the products and manufacturing track record were strong enough to grow even without a web presence. Awareness of that growth simply accumulated at the distribution layer that stood in for demand generation (Section 2.3). The substance is already proven; the one thing not yet attributed to us is awareness.

Second, the signal in timing. Recently there are cases of outside parties taking notice of our manufacturing and facility capabilities first (the Thermo Fisher collaboration). The track record has reached a threshold, and inbound interest is beginning. Yet a party who comes to us now and reaches our own channels to confirm finds nothing to take away. The number of published registration numbers is 0 (Section 1.1), and the certifications and track record we could show are already secured but not yet posted.

In conclusion, this strategy is not about inventing a new claim but about placing already-accumulated assets where they belong, so that the interest coming in resolves into confirmation. That is why we call this proposal a positioning strategy.

Table of Contents

Part 1 · Rebranding Direction

1. Executive Summary  ·  2. Situation Assessment  ·  3. Proposal to Shift the Axis  ·  4. Brand Architecture  ·  5. Supporting Evidence  ·  6. Language System  ·  7. Standard for Scale Claims

Part 2 · Realization on the Web

8. Role of the Web  ·  9. Realizing the Direction on the Web  ·  10. Implementation Schedule  ·  11. Prerequisites and Boundaries  ·  12. Items Requiring Approval

Appendices A. Research Method and Confidence System  ·  B. Registration Ledger  ·  C. Certification Verification Detail  ·  D. Operating Standards by Manufacturing Depth  ·  E. Full List of Restricted Expressions  ·  F. Competitor Production Capacity Survey  ·  G. Checklist Before Publishing to the Web

1. Executive Summary

1.1 The Problem

Three things are true of the current external message, and each can be confirmed within minutes.

| Point | Details |
| --- | --- |
| First | The phrase is not ours. 'We care for aging' is a sentence the cosmetics, filler, and health-functional-food industries all use identically. A sentence that every competitor can say together carries no distinguishing power, regardless of how polished it is |
| Second | We are not publishing our registration numbers. GANA R&D Co., Ltd. is listed as the manufacturer on 38 product registrations across 5 jurisdictions. The number of those registration numbers currently published on our own channels is 0. In their place sits 'Russia FDA approved', the name of an agency that does not exist |
| Third | A search for our own product name does not surface us. Distributor sites appear first. This is not brand infringement but an arithmetic outcome. For 13 years distributors performed demand generation, and awareness equity accumulated with the party that performed it |

The problem is not that we lack the credentials. It is that we are not using the credentials we hold.

1.2 The Solution

We do not change the claim. We attach proof to it. 'World's largest class' and anti-aging both stay, refined into a measurable and verifiable form that shuts down nitpicking at the source.

Not a filler company: bio-manufacturing infrastructure.

Most players in this market are brands that outsource manufacturing. We are not. In a B2B setting this distinction needs no separate explanation, and a competitor without a factory cannot copy it.

This shift does not eliminate the return question, 'how do you prove that.' It changes that question into 'show us the registrations,' to which we already hold the answer. What changes is not what we do, but what we ask people to believe.

1.3 Evidence

38 product registrations. 5 jurisdictions. GANA R&D Co., Ltd. listed as the manufacturer on every one.

Table 1. Product Registrations by Jurisdiction (as of 2026. 7. 22.)

| Jurisdiction | Agency | Count | Notes |
| --- | --- | --- | --- |
| United Kingdom | MHRA | 1 | Class III · UK Responsible Person designated |
| EU | EUDAMED | N/A | Manufacturer SRN KR-MF-000037221 · active |
| Brazil | ANVISA | 2 | Risk Class IV |
| Russia | Roszdravnadzor | 8 | 4 ingredient families + wound dressing |
| Korea | MFDS | 27 | 26 for export · manufacturing license · GMP valid through 2027. 3. 3. |

The 8 Russian registrations deserve a close look at their composition. Four distinct ingredient families, hyaluronic acid, PLLA, PCL, and calcium, are registered under a single manufacturer name. That breadth does not come from handling a single product line; it appears when a company performs compounding and filling across several chemical families.

What this evidence does not cover. None of the items above prove the cell and gene layer. That layer has not obtained cGMP and has no batch records. It is described separately in the ongoing tense in Chapter 3.

1.4 Prerequisite

There is one figure that must be settled before republishing. Batch capacity appears in our own materials as 5,000L, 6,000L, and 200,000L.

These are not three claims, but three points in time.

Each material was accurate when written and was not updated afterward. Press releases, the company site, and affiliate pages are each frozen at a different time.

The required action is narrow in scope. Until it is settled, no capacity figure goes into new external materials. This is closer to a freeze than a separate task, and work on the slogan, information architecture, and website proceeds in parallel, independent of it.

2. Situation Assessment

2.1 Structure of the Current Message

Table 2. What the Current Message Actually Triggers

| What we say | What they hear | What they do next |
| --- | --- | --- |
| Anti-aging care | An industry-standard phrase | Tune it out |
| Multiple affiliates | A count | Remember none of them |
| World's largest class facility | Something to verify | Compare it against competitor figures |
| Down to the gene level | A big promise | Demand proof |

The third column is the purpose of this table. It reduces an abstract diagnosis to observable behavior. In all four rows, the other party's next action works against us.

2.2 Assessment of External Channels

Table 3. Assessment of the Group's 3 Website Channels

| Channel | Verdict | Key findings |
| --- | --- | --- |
| ganarnd.co.kr | Full rebuild | Based on a 2013 builder template. A self-signed certificate triggers browser security warnings. No mobile support. Meta information neglected. Personal email exposed |
| gana-cosmetics.com | Partial cleanup | Has a design system, a B2B inquiry structure, and 4 languages. A candidate to elevate to the group standard. Needs work on search indexing, comparative wording, and claim scope |
| drpark-cdmo.com | Overhaul | A 2022 static site. Single language. Facility figures conflict within the site itself |

2.3 The Problem in the Demand-Generation Structure

When you search for our product name, official channels do not rank at the top; distributor sites appear first. This is not brand infringement but a structural outcome. For 13 years distributors carried out the demand-generation function, and correspondingly brand-awareness equity accumulated at the distribution layer.

Defined precisely, the task is not to 'reclaim the brand' but to 'move the demand-generation function in-house.' The first framing casts distributors as adversaries; the second specifies what we ourselves must do.

3. Proposal to Shift the Axis

3.1 Scope of Change

Nothing is removed. The 'world's largest class' facility, the six affiliates, and anti-aging all stay. What changes is how that claim is backed up. We attach a measurement standard (the ruler) and proof (registration numbers) so that saying it plainly does not cause it to collapse.

Anti-aging is not withdrawn; it is relocated. Internally it is retained as a purpose, and in the cosmetics line its external use continues as well. In that layer it is an accurate description and the very word dealers use to make actual sales. What changes is the group-level headline sentence, which moves from a shared category claim to a manufacturing position.

Table 4. Before and After the Axis Shift

| Item | Current | Proposed |
| --- | --- | --- |
| External subject | Aging (efficacy) | Manufacturer identity (fact) |
| Basis for differentiation | Breadth · largest scale | Manufacturer status (38 registrations · 5 jurisdictions) |
| Other party's next action | Demand proof | Look up the registration |
| Materials presented | None | Registration numbers · GMP certificate · factory |
| Burden of proof | On us | On us (same). Now fulfillable |

The burden of proof itself stays the same. What changes is that we now have the ability to meet it.

3.2 Application by Layer: Completed Tense and Ongoing Tense

The claim does not apply uniformly across the whole group. Each layer is described to the depth it can support.

Table 5. External Sentence and Evidence by Layer

| Layer | External sentence | Evidence |
| --- | --- | --- |
| Surface (fillers · materials) | "We made it." | MFDS 27 · RZN 8 · ANVISA 2 · GMP KCL-ABBA-19926 |
| Tissue (wound care) | "It is already registered." | RZN 2024/22431 · MFDS No. Jein 20-4997 |
| Cell · gene (AAV) | "We built it. Certification is targeted for 2026." | Completed 2025. 8. 5. · equipment named · joint release with supplier |

We do not write a sentence that ties the three layers under one subject. Bundling them lets the unproven layer drag even the proven layer into doubt. Since the asset value sits on the registration side, that trade does not hold.

3.3 Expected Effects of the Shift

Table 6. Expected Effects: Order of Occurrence

| Timing | Effect | Details |
| --- | --- | --- |
| Immediate | A lookup path in place | Every claim gains a lookup path. To a buyer who asks 'is that true,' we hand over a registration number, not an adjective |
| Within the sales cycle | From persuasion to confirmation | The nature of the conversation shifts. Confirmation favors the party holding the documents, and once the corrections in Chapter 12 are done, that party is us |
| Structural | Correction and branding unified | Because publishing the registrations is itself the execution of the axis, there is no path that merely tidies up without positioning |
| Incidental | Removal of a perceived hierarchy | 'Depth' is not a top-to-bottom ranking. The subjects handled simply differ, so no particular division is perceived as inferior |

4. Brand Architecture

We change the basis for introducing affiliates from 'level of intervention in aging' to 'manufacturing depth.' The affiliate lineup and order of importance stay the same; only the descriptive basis changes.

4.1 The 3-Layer Manufacturing-Depth Structure

Figure 1. The 3-Layer Manufacturing-Depth Structure: depth of the manufacturing target, not a top-to-bottom ranking

(Diagram: an illustration showing a manufacturing-depth structure made of three layers, surface, tissue, and cell/gene. It expresses the depth of the manufacturing target handled, not an up-and-down ranking.)

Reading the structure. This structure represents the depth of the manufacturing target, not a ranking. Layer 3 is not above Layer 1; the target handled is simply different. So the problem of a particular division being perceived as inferior does not arise.

※ The manufactured items, manufacturer, target customers, operating language, and performance indicators for each layer are compiled in Appendix D.

4.2 Placement of Affiliates

All affiliates are retained. What changes is the order of presentation. Entities that perform manufacturing come first, and entities responsible for supply and deployment come after.

Note. The total number of affiliates is settled only after the affiliate-scope confirmation (Chapter 11, Section 11.1) is complete. Because the set of entities using the group name currently differs from material to material, the number of affiliates is not disclosed in external materials until it is settled.

5. Supporting Evidence

This proposal rests on the results of a full sweep of public registries conducted on July 22, 2026. The research method and the confidence-notation system are compiled in Appendix A.

5.1 Registration Summary

In the public database of Russia's Federal Service for Surveillance in Healthcare, we confirmed 8 valid registrations listing GANA R&D as the manufacturer. The manufacturer name and location match, and there is no mixing with another company of the same name. Four ingredient families, hyaluronic acid, PLLA, PCL, and calcium, and a wound dressing are included.

Notation caution. We do not use the phrase 'registered under our name.' The registration holder for the 8 items is a local agent, and GANA R&D is listed in the manufacturer field. The accurate phrase is '8 registrations listing us as the manufacturer.' In this proposal, which takes manufacturer identity as its axis, this phrasing is both more accurate and stronger.

Current state of use. The website today lists no registration numbers at all and posts only the phrase 'Russia FDA approved.' 'Russia FDA' is the name of an agency that does not exist; the actual agency is Russia's Federal Service for Surveillance in Healthcare. Replacing this phrase with the 8 registration numbers and lookup links is the single biggest improvement available at no additional cost.

5.2 Verification Summary

Table 7. Verification Results for Externally Stated Certifications (Summary)

| Category | Items |
| --- | --- |
| Valid · usable | 8 Russian registrations · MFDS GMP conformity (through 2027. 3. 3.) · 27 MFDS product approvals · UK MHRA Class III · EU EUDAMED manufacturer registration · 2 Brazil ANVISA |
| Expired (stop publishing) | EU CE certificate (expired 2024. 5. 27.) · ISO certificate |
| Notation error (correct immediately) | 'Russia FDA' · 'FDA approved / Registered' · 'KFDA' |
| Unconfirmed (do not use) | US FDA medical device registration · ISO 13485 / 22716 originals |
| Not verifiable by design | EU CPNP (not attributable to us) |

※ Detailed evidence and lookup paths for each item are in Appendix C. 'Not verifiable' does not mean absence of registration.

5.3 Items for Immediate Correction (Site Notation)

The full list of correction items and the order of execution are compiled in Section 9.2. This section specifies the priority correction items among the notations currently published on the site.

| Current notation | Correction |
| --- | --- |
| 'Russia FDA approved' | Name of a nonexistent agency. Replace with actual registration numbers + lookup links |
| 'FDA approved' · 'FDA Registered' (including within product names) | Registration is not approval. Delete or state the nature of the registration |
| Expired certification badges | Take down + post the current GMP certificate. Using the credentials you hold grows the asset |

6. Language System

6.1 Conditions for Writing the Slogan

This section does not finalize the copy. The slogan copy is written after the axis in Chapter 3 is approved. Finalizing the copy first, without the axis set, would force a full rewrite when the axis changes. This edition defines only the conditions the copy must satisfy.

Table 8. Conditions for Writing the Slogan

| No. | Condition |
| --- | --- |
| 1 | The predicate must be the center of the sentence. Using a range expression ('from surface to cell') on its own reverts to the very 'breadth' frame we are discarding |
| 2 | Do not tie the two ends under one subject. Copy that violates the layer-by-layer tense in Section 3.2 is not adopted |
| 3 | Separate by affiliate. Do not use the group copy and the cosmetics-division copy identically. The cosmetics division keeps its anti-aging expression |
| 4 | Use the singular entity as the subject. Do not use the group as a single subject until the capital relationships are confirmed |
| 5 | The English version is the master. Do not finalize the Korean first and then translate. Copy that does not stand up in English is not adopted |

6.2 Summary of Usage Restrictions

The full list of restricted expressions is compiled in Appendix E. This section specifies only the items newly added in the 2nd Edition.

| Expression | Category | Reason |
| --- | --- | --- |
| 'Registered under our name' | Prohibited | The registration holder is a local agent. 'Listed as the manufacturer' is the accurate phrase |
| Claim of synthesizing raw materials in-house | Prohibited | Asset ledger unconfirmed. Registration proves manufacturing scope but does not prove raw-material synthesis |
| Unsettled capacity figures | Frozen | Section 11.1. No publishing in new materials before it is settled |
| Group as a single subject | On hold | Prohibited until capital relationships are confirmed |

7. Standard for Scale Claims

The 'world's largest class' expression is retained. We do not delete it; we attach a measurement standard (the ruler) so it cannot be nitpicked in due diligence. The issue is not the superlative itself but the form where there is no measurement axis or where our own figures conflict. The competitor capacity survey is compiled in Appendix F.

Why the current notation gets nitpicked, and how to resolve it. a. No measurement axis: 'World largest AAV vector CDMO' does not state what it is largest by. Viralgen makes the same claim on a total-facility basis. Stating an axis such as 'single batch' makes the conflict disappear. b. Conflicting internal figures: 5,000/6,000/200,000L. What nullifies the superlative is not a competitor but the conflict in our own statements, so it is resolved by a figure freeze (Section 11.1). c. Unsurveyed players: the single-batch capacity of many large CDMOs is unconfirmed. Until confirmed, keep the 'one of ~' form, and after confirmation elevate it to a definitive form.

Table 9. Scale-Claim Tiers: retain, but choose the form

| Tier | Wording | Conditions · basis |
| --- | --- | --- |
| Usable | "one of the world's largest and most advanced AAV production capacities" (our own video copy) | Qualified by 'one of' · Forge Biologics uses an equivalent expression · already published in a chairman-approved video |
| Usable | "World's largest class Phase 1 facility by AAV production design capacity (completed August 2025, cGMP targeted for 2026)" | Measurement axis (design capacity) + tense stated |
| Supporting | "The largest publicly disclosed single batch is 2,000L, and our design capacity exceeds it" | Presents competitor figure + comparison to ours |
| Use after softening | "World largest AAV vector CDMO" (unqualified superlative) | No measurement axis. Soften with 'one of ~ class' or by stating the axis |
| Elevate (future) | "World's largest single batch" (definitive) | After the figure is settled + WuXi, Catalent, and Charles River are confirmed |
| Frozen | Unsettled batch capacity figures | Section 11.1 (to prevent conflict in our own statements) |

Stating the tense is mandatory. Expansion plans are not current operating capacity. Presenting planned capacity as current fact loses trust with a single on-site inspection.

Scale is not presented on its own but together with its purpose. Because a major bottleneck in gene-therapy cost is the unit cost of vector manufacturing, increasing batch scale leads to lower cost per dose. Stating this causal link makes scale function as evidence rather than a headline.

8. The Role of the Website

Part 1 (Chapters 1 to 7) defined the direction of the rebranding. Part 2 addresses how that direction becomes real on the website. This is also the work originally commissioned: the scope of the web rebuild.

The premise of Part 2. The new axis is this: stop explaining ourselves and hand over the numbers. A sentence is a claim, and the website is where those numbers are actually handed over. When a buyer asks "is that true?", the site is where they come to check. That is why the web rebuild is not a side branch of this plan but the point where the axis turns into fact.

8.1 Where the Evidence Lives

The new axis comes down to one thing: when asked, hand over the registration record. The site is where that handing over actually happens.

Table 10. Registration Postings: Current State and Target

| Current state | What it should be |
| --- | --- |
| 38 product registrations, 0 numbers posted on the site | A registration number and lookup link attached to every product |
| "Russia FDA approved" in their place (an agency that does not exist) | Replaced with real registration numbers (RZN, MHRA, ANVISA, MFDS) |
| Expired certification badges posted | Expired items removed, current GMP certificates posted |

This is the single item in the entire plan with the highest return for the effort. It is pure web work and the cost is zero. This one task turns the axis from words into fact.

New: Certification and Registration Library (Section 9.1). A single page that gathers registration numbers and lookup links by jurisdiction. It becomes the first page auditors, buyers, and analysts open.

8.2 Bringing Demand Generation In-House

For 13 years, distributors handled demand generation on our behalf. As a result, searching for our own product names surfaces the distributor sites ahead of ours. This is not a case of the brand being infringed but a result the structure produced, and it is corrected on the web.

Figure 2. Exposure Structure: The Serial Relationship Between Discovery (Search) and Confirmation (Registration)

Being discovered first through search and then confirmed through registration are two stages linked in series. When the discovery stage has been handed to distributors, traffic leaks away before it reaches the confirmation stage. The key is returning the point of discovery to our own channels.

Table 11. Web Cleanup to Recover Search

| Current state (all web) | Action |
| --- | --- |
| Self-signed certificate, causing security warnings | Replace with proper SSL |
| Personal email, no domain email | Switch to domain email |
| Fragmented English naming (R&D / RND / Gana R&D) | Single English name to consolidate search |
| Meta and preview data neglected, no mobile support | Clean up search indexing, make responsive |

Added to this is the search authority that regulatory agency domains carry. When registration numbers and lookup links are placed on the site, those links push distributor pages down in search rankings. The web is precisely the means that carries out the direction of "bringing the demand generation function in-house."

8.3 Manufacturing Depth = Information Architecture

The manufacturing depth of "surface to tissue to cell" is not a logic built for a presentation but the information architecture (IA) of the site itself. Listing the six companies flat makes them look like a buffet, but making manufacturing depth the axis turns them into a single flow, with the companies that make things standing in front and the companies that deploy them following behind.

An asset we already have. Among the six sites, gana-cosmetics.com is the only one that works properly. It already has a design system, a B2B inquiry structure, and four languages. We raise this site to the group standard and rebuild the parent-company site on top of it. The design original for the rebranding is not something to buy from outside: it is already within us.

9. Realizing the Direction on the Web

This maps how each direction defined in Part 1 is implemented as a specific element on the site.

Table 12. Mapping the Rebranding Directions to Web Implementation

| Rebranding direction (Part 1) | Implementation on the web |
| --- | --- |
| Axis: the manufacturing entity (Chapter 3) | Rewrite the home headline and About from "explanation" to "presenting the manufacturing record" |
| Tense by layer, completed / in progress (3.2) | Three-layer IA: surface and tissue as product registration pages (completed tense), cell as a "facility under construction" page (in-progress tense) |
| 38 items of evidence across 5 jurisdictions (Chapter 5) | Certification and Registration Library: registration numbers plus lookup links by jurisdiction |
| Accurate wording of "listed as manufacturer" (5.1) | Standardize product-page labels to "registered as manufacturer." Do not use "registered under our name" |
| Language system (Chapter 6) | Apply the copy guide to all page text, reflect the restricted-expression glossary |
| Scale expression (Chapter 7) | State design capacity plus tense on the facility page. Frozen figures are not posted |
| Placement of anti-aging (3.1) | The cosmetics site keeps anti-aging, the parent company holds the manufacturing axis |
| Order of affiliates (Chapter 4) | Navigation: manufacturing entities first, deployment entities after |
| Bringing demand generation in-house (2.3) | Recover search through domain email, single naming, SSL, meta data, and registration links |

9.1 New: Certification and Registration Library

This is the core deliverable of Part 2. A single page gathering registration numbers and lookup links by jurisdiction, it becomes the first place auditors, buyers, and analysts open. It is the page where the answer to the new axis's "show me" physically exists, and the registration ledger (Appendix B) becomes the direct source for this page.

9.2 Immediate Web Cleanup (No Approval Needed, Zero Cost)

These are all web tasks that erase incorrect wording or take down expired items, so they can proceed now regardless of whether the axis is decided.

| No. | Item |
| --- | --- |
| 1 | Fix the security certificate (remove the browser security warning) |
| 2 | Take down expired certification badges, post current GMP certificates |
| 3 | "Russia FDA" to real registration numbers plus lookup links |
| 4 | Delete "FDA approved / Registered," change "KFDA" to "MFDS" |
| 5 | Switch to domain email, remove exposed personal email |
| 6 | Apply a single English name, standardize address and postal code |
| 7 | Meta information and mobile support |

10. Rollout Schedule

The guiding principle is "clean up first, then expose." Increasing exposure before the cleanup is finished backfires.

Figure 3. Rollout Schedule: Moving to the Exposure Stage After Cleanup Is Complete

The stages run in sequence from P0 through P4. They are arranged so that external exposure expands only after cleanup is finished, preventing a situation where traffic pours in before things are ready.

Table 13. Rollout Content by Stage

| Stage | Duration | Rollout content |
| --- | --- | --- |
| P0 | 1 week | Immediate web cleanup (all items in Section 9.2). Security certificate, domain email, expired badges, "Russia FDA" to registration numbers, post current GMP |
| P1 | 2 to 4 weeks | Confirm the brand axis, slogan, codify the copy guide, promote the design standard (cosmetics system), naming glossary |
| P2 | 4 to 8 weeks | Full rebuild of the parent-company site, Certification and Registration Library, three-layer IA restructuring, six languages / (in parallel) cosmetics site cleanup |
| P3 | 3 to 5 weeks | Dr.Park CDMO site overhaul (begins after the figures are confirmed) |
| P4 | After that | Cleanup of affiliate links, launch of third-party channels (academic societies, industry reports) |

11. Prerequisites and Boundaries

This separates the items that must be confirmed before web execution from the items outside web scope that this proposal does not address.

11.1 Confirm Before Reflecting on the Web (Before Posting to the Site)

| Item | Handling |
| --- | --- |
| Batch capacity figures (5,000 / 6,000 / 200,000L) | Not posted on the site until confirmed (frozen). The remaining web work proceeds in parallel |
| Official English product naming | Applied across all pages at once after the naming glossary is confirmed |
| Affiliate scope and order | Reflected in navigation after confirmation. The number of affiliates is not stated before confirmation |
| Citation of contract-manufactured brands | Whether third-party brand products (such as UK Class III) may be cited externally is set by contract. Posted after confirmation |

11.2 What Is Not Web, Outside This Proposal's Scope

Principle. Unconfirmed or unverified items are not posted on the site. Only what is verified goes on the web. This principle itself connects to the axis ("say only what can be verified"). During the research, items outside web scope were also observed, such as corporate and asset relationships and the expiry and renewal of regulatory registrations. Because these fall under the regulatory, legal, and management functions, this proposal does not address them; they are separated from the web work and passed to those functions.

12. Approval Requests

These requests are limited to web scope.

Request 1  |  Begin Immediate Web Cleanup (No Approval Needed, Zero Cost)

These are the seven items in Section 9.2. Since all of them erase incorrect wording or take down expired items, they begin at once regardless of whether the axis is decided.

Request 2  |  Align External Wording (Keep + Prove)

Add the manufacturing-entity (proof) axis to the slogan, home headline, and information architecture. Keep the existing positioning but rewrite it in a defensible form.

| Item | Content |
| --- | --- |
| "World's largest class" | Keep. Use the form from our own video copy, "one of the world's largest … AAV production capacities," plus a stated measurement axis (Chapter 7) |
| Anti-aging | Keep. Retained as a purpose layer and as external wording for the cosmetics division |
| Application rule | Layers 1 and 2 in completed tense, layer 3 in in-progress tense. Do not join the two ends under a single subject |
| Operating rule | Batch capacity figures are not posted on the site until confirmed |

Request 3  |  Promote the Cosmetics Design System to the Group Standard

Take the design system and multilingual structure of gana-cosmetics.com as the group standard, and rebuild the parent-company site on top of it.

The basis for introducing affiliates changes from "level of aging intervention" to "manufacturing depth." It is reflected in navigation only after the affiliate scope and order are confirmed.

Request 4  |  External Wording Review Process

External regulatory wording posted on the site reflects only what has passed the check of the responsible functions (regulatory, legal). Marketing and web draft the text.

No asset is discarded. On the web, we stop explaining ourselves and now begin to hand over the numbers.

Appendix A. Research Method and Reliability Framework

| Item | Content |
| --- | --- |
| Research date | July 22, 2026 |
| Research scope | Public registry listing status of the group's legal entities, competitor production capacity, and verification of unconfirmed items |
| Research method | Direct queries of regulatory agencies' public databases, review of official website source text, and comparison against original press release wire copy |
| Research principles | Exclude estimation, attach a public query path to each positive result, record the search terms and date of each negative result, and exclude other companies bearing the same name |

A.1 Reliability Notation System

| Notation | Definition | External Use |
| --- | --- | --- |
| Confirmed | Public primary source or direct registry query | May be used |
| Self-claimed | Only the company's own wording exists, with no third-party verification | Limited use after softening |
| Unconfirmed | Researched but could not be confirmed (distinct from absence of a listing) | Not to be used |

A.2 Primary Sources

Roszdravnadzor (Russian Federal Service for Surveillance in Healthcare) public medical device registration database

Korea MFDS (Ministry of Food and Drug Safety) medical device e-civil complaint portal: business license, GMP conformity certification, and product approval

UK MHRA public register, EU EUDAMED, and Brazil ANVISA

UK Companies House: registration information for affiliated legal entities

US FDA Establishment Registration & Device Listing and openFDA

Competitor official websites and press releases: Viralgen, Forge Biologics, Minaris, Catalent, Charles River, AGC Biologics

Comparison against original press release wire copy and 15 redistributing media outlets

Appendix B. Listing Ledger

B.1 Roszdravnadzor (Russian Federal Service for Surveillance in Healthcare), as of July 22, 2026

| No. | Registration No. | Product | Registration Date | Layer |
| --- | --- | --- | --- | --- |
| 1 | RZN 2021/14277 | GANA HA (A/B/C), hyaluronic acid | 2021-05-07 | 1 |
| 2 | RZN 2021/13973 | GANA X / V, PLLA | 2021-04-08 | 1 |
| 3 | RZN 2022/18121 | GANA HA Body | 2022-08-29 | 1 |
| 4 | RZN 2024/22431 | GANA PATCH, hydrogel wound dressing | 2024-04-18 | 2 |
| 5 | RZN 2024/22440 | GANA BOOSTER, HA | 2024-04-23 | 1 |
| 6 | RZN 2024/22794 | GANA PH, PLLA + HA | 2024-05-30 | 1 |
| 7 | RZN 2025/26343 | GANA Filler X, PCL + HA | 2025-11-19 | 1 |
| 8 | RZN 2025/26344 | GANA CH, calcium + HA | 2025-11-19 | 1 |

Note: The manufacturer field matches GANA R&D for all 8 entries. Because the registered holder is a local representative, the phrasing "registered under our name" is not to be used.

B.2 Other Jurisdictions

| Jurisdiction | Identifier | Content |
| --- | --- | --- |
| UK MHRA | Manufacturer listing / 1 device | Class III, UK Responsible Person designated. The brand is owned by the contracting party, so public citation of the brand name is possible only after contract confirmation |
| EU EUDAMED | KR-MF-000037221 | Manufacturer registration active |
| Brazil ANVISA | 2 entries, risk class IV | The registration holder is the local entity, and the manufacturer field is the company |
| Korea MFDS | 27 product approvals | 26 are limited to export use. 1 for domestic use (제인20-4997) |

B.3 Manufacturer Qualification Listings

| Item | Number | Status |
| --- | --- | --- |
| MFDS manufacturing license | No. 4490 | Normal (March 5, 2014) |
| MFDS GMP conformity certification | KCL-ABBA-19926 | Valid through March 3, 2027 |
| MHRA manufacturer listing | MAN_ID 32678 | Last updated April 11, 2026 |
| EUDAMED Actor | KR-MF-000037221 | Manufacturer / active |

Appendix C. Certification Verification Details

| Item | Result | Content |
| --- | --- | --- |
| Russia Roszdravnadzor | Confirmed (8 entries) | Direct query of the public database. Manufacturer name and location match |
| MFDS GMP conformity certification | Valid | KCL-ABBA-19926 (through March 3, 2027). A current version exists, but the site is posting the expired version |
| MFDS product approval | Confirmed (27 entries) | 26 are limited to export use. The scope must be stated because it could be mistaken for domestic sales approval |
| UK MHRA | Confirmed | Manufacturer listing, 1 Class III device |
| EU EUDAMED | Confirmed | Manufacturer SRN active |
| Brazil ANVISA | Confirmed (2 entries) | The registration holder is the local entity, and the manufacturer field is the company |
| EU CE certificate | Expired | Expired May 27, 2024. The expired badge on the site is to be taken down |
| US FDA medical device | Not registered | Another company at the same building address is listed normally, but a search for the company returns no result |
| FDA Registered (cosmetics) | Different scope | This is a voluntary registration scheme, not an approval. Company-wide notation is not permitted |
| ISO 13485 / 22716 | Unconfirmed | Not found in international certification searches. The original document and issuing body must be verified |
| EU CPNP | Cannot be verified | Non-public by scheme design. Not attributable to the company |

Appendix D. Operating Criteria by Manufacturing Depth

| Category | Layer 1 (Surface) | Layer 2 (Tissue) | Layer 3 (Cell / Gene) |
| --- | --- | --- | --- |
| Manufactured products | HA, PLLA, PCL, calcium, PDRN | Biocellulose wound dressing | AAV vector, plasmid, protein |
| Manufacturing entity | GANA R&D | GANA R&D | Dr.Park CDMO |
| Supporting evidence | 7 RZN entries, 27 MFDS entries | RZN 2024/22431, MFDS 제인20-4997 | Construction completion record, equipment installation |
| Tense | Completed | Completed | In progress |
| Target customers | Distributors, medical institutions, ODM | Regulatory agencies, medical distribution | Pharma / bio, investors |
| Communication tone | Commercial B2B | Regulatory, clinical | Corporate, investor |
| Operating languages | 6 languages | English | English (with Chinese in parallel) |
| Performance metrics | Number of inquiries, number of distributors | Number of registered countries | Number of mentions, listings, and invitations |

Appendix E. Complete List of Restricted Expressions

| Expression | Category | Reason |
| --- | --- | --- |
| "FDA approved", "FDA Registered" | Prohibited | Registration is not approval. The item with the greatest legal exposure |
| "Russia FDA" | Prohibited | A nonexistent agency name |
| "KFDA" | Prohibited | A name abolished in 2013. The current name is MFDS |
| Notation of expired certifications | Prohibited | CE and ISO expirations confirmed |
| Superlative expressions without basis | Prohibited | Creates a burden of substantiation (Chapter 7) |
| "registered under our name" | Prohibited | The registered holder is a local representative. "listed as manufacturer" is accurate |
| Claims of in-house raw-material synthesis | Prohibited | Not confirmed in the asset ledger. A listing proves manufacturing scope but does not prove raw-material synthesis |
| Direct comparison with other companies' products | Prohibited | Labeling / advertising and comparative advertising regulations |
| Unconfirmed capacity figures | Frozen | Section 11.1. No new material to be posted before confirmation |
| Group as a single subject | On hold | Not to be used before the capital relationship is confirmed |
| Pharmaceutical-grade efficacy expressions | Restricted by market | The cosmetics segment requires jurisdiction-specific qualifiers. Legal review before confirmation |
| Food-service analogy expressions | Internal only | Insufficient cross-language applicability. Reduces credibility at Layer 3. Implies in-house raw-material production, so use creates a burden of substantiation |
| "Partnership" (equipment supply) | Use with caution | In reality it is equipment purchase and supplier selection. Over-broad interpretation backfires in due diligence |

Appendix F. Competitor Production Capacity Research

AAV single-batch capacity (based on official sources)

| Operator | Single Batch | Basis of Superlative Claim |
| --- | --- | --- |
| Viralgen | 2,000L | Based on total production capacity and facility area |
| Forge Biologics | 5,000L | "one of the largest" (no superlative claimed) |
| Minaris | 2,000L | Quality basis (world-class) |
| Catalent | 2,000L | Based on cell therapy and area, no superlative claimed |
| Charles River | 500L | Not applicable |
| AGC Biologics | 2,000L | Not applicable |
| Dr.Park CDMO | Before confirmation (11.1) | Not applicable |

The maximum public figure among the operators researched is 2,000L, and no operator claims a superlative on an 'AAV single-batch' basis. Because many large CDMOs remain unresearched, a superlative at 'world' scope does not hold.

Appendix G. Items to Confirm Before Web Publication

The following are items requiring confirmation before posting to the site. Until confirmed, the relevant content is not to be posted.

| No. | Subject | Reason for Confirmation |
| --- | --- | --- |
| 1 | Affiliate scope and order | The scope of entities using the group name differs across materials. Reflect in navigation after confirmation |
| 2 | Whether contract-manufactured brands may be cited | Whether the manufacturing record of another company's branded product (UK Class III, etc.) may be cited externally is governed by contract |
| 3 | Confirmed batch capacity figure | The authoritative figure among 5,000 / 6,000 / 200,000L. Not to be posted on the site before confirmation |
| 4 | Competitor single-batch capacity (large CDMOs) | Official materials not disclosed. A precondition for using scale superlative expressions |

This second edition of the proposal was prepared as of July 23, 2026. Unconfirmed items have been explicitly distinguished and recorded, and as a matter of principle unconfirmed items are not used in external communications. This document is for internal review and external distribution is prohibited.